## Mine (so far)
[16 empty] | Week 1 |  | 0 | Week 1 |  | 0
[17 empty] | Overview | -3 |  | Overview | 3
[16 empty] | Week 2 | Storyboard/UI design | 2 | Week 2 | Storyboard/UI design | 2
[18 empty] | 0 |  |  | 0
[16 empty] | Week 3 |  | 0 | Week 3 |  | 0
[18 empty] | 0 |  |  | 0
[16 empty] | Week 4 | Interview | 4 | Week 4 | Interview | 4
[17 empty] | Storyboard/UI design | -3 |  | Storyboard/UI design | -3
[16 empty] | Week 5 | Project Plan | 2 | Week 5 | Project Plan | 2
[17 empty] | Presentation video | -4 |  | Presentation video | -4
[17 empty] | Website Report | 3 |  | Website Report | 3
[16 empty] | Week 6 | Reflection (for the plans) | 5 | Week 6 | Reflection (for the plans) | 5
[17 empty] | Project App | -2 |  | Project App | -2
[16 empty] | Week 7 |  |  | Week 7
[16 empty] | Week 8 |  |  | Week 8
[16 empty] | Week 9 |  |  | Week 9
[16 empty] | Week 10 |  |  | Week 10
[16 empty] | Week 11 |  |  | Week 11
[16 empty] | Week 12 |  |  | Week 12
[16 empty] | Week 13 |  |  | Week 13
[16 empty] | Week 14 | Test and edit App | 2 | Week 14 | Test and edit App | 2
[17 empty] | Reflection(for the app) | -2 |  | Reflection(for the app) | 1
[16 empty] | Week 15 | Publish App | 4 | Week 15 | Publish App | 2
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Project Plan | bar: Week 1 to Week 5
Overview | bar: Week 1 to Week 2
Storyboard/UI design | bar: Week 3 to Week 4
Presentation video | bar: Week 3 to Week 5
Website Report | bar: Week 2 to Week 5
Interview | bar: Week 2 to Week 4
Reflection (for the plans) | bar: Week 6
Project App | bar: Week 6 to Week 15
Test and edit App | bar: Week 12 to Week 14
Reflection(for the app) | bar: Week 14
Publish App | bar: Week 15

## Timeline with Job Allocation
WEEK | MILESTONE | ALLOCATION
Week 1 | 1. Generate App idea
| 1a. Brainstorm | Team
| 1b.Meet to plan report writing allocation - Initial Draft | Team
| Overview and Project Idea and Aim | Chris
| Comparison of Careers and Ideal Jobs | Troy
| Timeline | Fawaz
| Storyboard | Sasha
Week 2 | 2. Writing Out Features
| 2a. Meeting to update | Team
| 2b. Draft of Project Overview | Chris
Week 3 | 2. Writing Out Features
| 2b. Draft of Project Overview | Chris
| 2c. Storyboard | Sasha
| 2d. Timeline table and job allocation drafted | Troy
| 2e. Design Prototype | Andrew
| 2f. Plan Interview | Team
| 2g. GUI Flowchart | Sasha
Week 4 | 3. Design Mock-up | Sasha and Andrew
| Update Prototype | Andrew
| Update Timeline | Fawaz
Week 5 | Design Mock-up | Sasha and Andrew
| Layout design for apps homepage and index | Sasha
| Test functionality via Adobe XD | Andrew
| Final Report | Chris
Week 6 | Finalise Writing Out Features | Chris
| Compare Market for App | Fawaz and Troy
| Draft Marketing Plan | Fawaz and Troy
| Creating Graphic Design | Andrew and Sasha
| Build the App | Project Manager
| Front End Development | Team
| Back-end Development | Team
Week 7 | Market App | Business Analyst
| write marketing descriptions | Chris
| explore funding options | Fawaz
Week 8 | Market App | Business Analyst
| develop SEO | Fawaz
| Contact Vendees and Sponsors | Fawaz
Week 9 to Week 12 | Build the App | Team
| Front End Development | Troy
| develop user-facing features; | Chris
| test functionality | Andrew
| optimize app | Andrew
| validate input | Troy
| review | Chris
| Back-end Development | Andrew
| write initial endpoints for front and back ends | Mobile App Developer
| design API | Mobile App Developer
| refine database and implement | Sasha
| backend test script | Andrew
| implement API | Mobile App Developer
| deploy | Troy
| review | Chris
Week 13 | Testing and Update | Mobile App Developer
Week 14 | Testing and Update | Mobile App Developer
Week 15 | Launch App | Project Manager
Launch app
Test App
Improve with user feedback

## Troy's
[16 empty] | Week 1 | Generate App idea | 6
[17 empty] | Report Writing | -3
[16 empty] | Week 3 | Writing out the features | 2
[17 empty] | Compare Market for App | -6
Week 4
[16 empty] | Week 5 | Report Writing | 2
[17 empty] | Design Mockup | -3.5
[16 empty] | Week 6 | Writing out the features | 7
[17 empty] | Compare Market for App | -6
[17 empty] | Build the app | 3
[16 empty] | Week 7 | Creating graphic design
Week 8
Week 9
Week 10
[17 empty] | Market app | 2
Week 11
Week 12
Week 13
Week 14
[16 empty] | Week 15 | Finishing Front-end Development | 6
[17 empty] | Finishing Back-end development | -8
[17 empty] | Test App | -4
[17 empty] | Improve with user feedback | 7
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Generate App idea
Writing out the features | Chris
Compare Market for App
Design Mockup
Report Writing
Creating graphic design
Build the app
Front-end Development
Back-end development
Test App
market app
Improve with user feedback
Person A